## exhibit index
EXHIBIT INDEX
Exhibit No. | Description
99.1 | Iris Energy Limited, December 2021 Monthly Investor Update, dated January 11, 2022

## signatures
SIGNATURES
Iris Energy Limited
Date: January 11, 2022 | By: | /s/ Daniel Roberts
Daniel Roberts
Co-Chief Executive Officer and Director

## operating and financial re
Operating and Financial Results
Operating* | Oct-21 | Nov-21 | Dec-21
Operating renewable power usage (MW) | 22 | 23 | 26
Avg operating hashrate (PH/s) | 649 | 657 | 748

## operating and financial re-1
Financial (unaudited) | Oct-21 | Nov-21 | Dec-21
Bitcoin mined * | 127 | 113 | 124
Mining revenue (US$'000) 4 | 7338 | 6593 | 6170
Electricity costs (US$'000) 4 | 852 | 822 | 945
Revenue per Bitcoin (US$) | 57634 | 58328 | 49700
Electricity costs per Bitcoin (US$) | 6695 | 7275 | 7612

## operating and financial re-2
Miner Shipping Schedule | Hardware | Units | PH/s (incremental) | PH/s (cumulative)
Operating (December 2021) | S19j Pro / A12 / Other 5 | 8362 | 748 | 748
Inventory – in transit | S19j Pro / S19j | 4971 | 485 | 1233
Inventory – pending deployment | S19j / Other 6 | 2690 | 219 | 1452
Q1 2022 | S19j Pro / S19j | 11584 | 1112 | 2564
Q2 2022 | S19j Pro / S19j | 11660 | 1119 | 3683
Q3 2022 | S19j Pro / S19j | 7063 | 659 | 4342
Q4 2022 | S19j Pro / S19j | 27973 | 2781 | 7123
Q1 2023 | S19j Pro | 26577 | 2658 | 9781
Q2 2023 | S19j Pro | 26765 | 2676 | 12457
Q3 2023 | S19j Pro | 26952 | 2695 | 15152
Total |  | 154597 | 15152

## operating and financial re-3
Site Overview | Capacity (MW) | Capacity (EH/s) | Timing | Status
Canal Flats | 30 | 0.7 | Complete | Operating
Mackenzie | 50 | 1.5 | Q2-Q3 2022 | Under construction
Prince George | 85 | 2.4 | Q3 2022/2023 | Under construction
Other secured sites | 365 | 10.6 | TBC | Under development
Total | 530 | 15.2